## Timeline_Milestones
Phase | Weeks (T+) | Exit Criteria | Notes
A. Governance & Prep | 0–1 | Charter signed; Teams/SharePoint live; risks logged
B. Foundation (CF/SetIDs/BUs/Trees/Banks) | 1–3 | CF values & Trees loaded; 5 EU BUs created; bank shells created
C. Module Build (GL/AP/AR/BI/AM/PC) | 3–7 | Config walkthroughs passed; AWE paths in place
D. Integrations Build (files) | 5–10 | JRNL_LOAD, Voucher Build, BI Loader, EBS jobs runnable end‑to‑end
E. Conversion #1 (masters) | 6–8 | Customers, suppliers, banks load clean
F. Conversion #2 (history + open items draft) | 9–12 | TB variance ≤ 0.5%; sample FA & open AP/AR load
G. SIT (E2E + interfaces + bank rec) | 12–16 | ≥ 95% pass; no Sev‑1 defects
H. Conversion #3 (cut‑over loads) | 16–18 | Final open AP/AR/FA; GL deltas posted
I. UAT (business sign‑off) | 16–20 | All critical scenarios signed; ≤ 5 Sev‑2 open
J. Parallel Close (one period) | 20–22 | GL variance ≤ 1%; CFO sign‑off
K. Cut‑over & Go‑live | 22–23 | Checklists green; first batch healthy
L. Hyper‑care (30 days) | 23–27 | KPIs stable: close ≤ 5d; auto‑rec ≥ 95%; < 50 manual JEs

## Workstreams_Owners
Workstream | Owner | Backup | Contractor Augmentation | Notes
Billing & AR | Naveen | Jalaj
Accounts Payable | Jalaj | Satish | Add 0.3 FTE AP analyst (weeks 5–12)
Treasury/Payments & Bank Rec | Satish / Karthick | Niranjan
General Ledger & Close | Niranjan | Satish | Add 0.2 FTE GL functional (weeks 5–12)
Asset Management | Jalaj | Niranjan
Indirect Tax (VAT/GST) | Jalaj | Durga (interfaces)
Coupa Procurement | Ant / Sainath | Jalaj | Add 0.3 FTE Coupa tech (weeks 5–12)
Integrations/Middleware | Vicky (design) / Durga (build) | —
Reporting/BI | Durga | Niranjan
Env & DevOps | Durga | Vicky

## Foundation_Build
Task | Details | Owner | Acceptance
SetIDs & BUs | Create SetID SHARE; define 5 GL/AP/AR/BI/AM BUs (UK, Muzicall UK, AT, PT, HR) | Sys Admin | BUs visible in unit control; SetID mapped
ChartFields | Load Account/Dept/Division/Product via ExcelToCI; compile NAT_ACCT/Dept/Division/Product Trees | GL Lead / Data | Trees compile; no orphans
Calendars & FX | Assign 12‑period calendar; define rate types AVG/CRRNT/HIST | GL Lead | Rates load successfully
Banks | Create bank shells (BofA x9025/x9017, BofA x7018, BofA x6018, Bankinter x7776, mojaRBA) | Treasury | Accounts mapped to BUs
VAT skeletons | Seed VAT structures for UK/AT/PT (rates later) | AP/Billing Leads | Structures saved

## Module_Config
Module | Key Config Items | Acceptance
General Ledger | Ledger Group ACTUALS; (optional) Multi‑Book; AWE thresholds; reval/translation; Trees for nVision | Unit JE posts; nVision TB runs
Accounts Payable | Voucher Build; 2/3‑way match; VAT defaults; Payment Dispatch (BACS/SEPA/ACH); AWE approvals | Sample voucher posts; payment preview OK
AR / Billing | BI_INTFC_STG → Billing Loader; BI Publisher invoices; email & portal; GL posting for AR/Revenue/VAT | Invoice finalised; PDF generated; GL posted
Asset Management | AM BUs; CORP (STAT if needed); profiles; depreciation; FA → GL; optional CIP from PC | Depreciation test posts
Purchasing | POs where used; copy CFs; receiving rules for services vs goods | PO→AP path validated
Project Costing | BUs; statuses (PLN/ACT/CLS); Rate Sets (COST→BILL/CAP) | Rate set used in test project

## Integrations
Feed | Direction | Method | Owner | Success (Done when)
Coupa → AP | Inbound | CSV/API → Voucher Build | Integrations / AP | Voucher posts; error report archived
Invoice CSV → Billing | Inbound | Excel → BI Loader | Billing / Integrations | Invoice finalised; PDF; GL posted
Bank statements | Inbound | EBS Loader (MT940/CAMT/BAI2) | Treasury / Integrations | Auto‑rec ≥ 95% on sample day
Payments | Outbound | Payment Dispatch (BACS/SEPA/ACH) | AP / Treasury | Bank accepts file; remittance proof
GL residuals | Inbound | JRNL_LOAD | GL / Integrations | Journal posts via AWE

## DataConv_Gates
Gate | Must be true before… | Why it gates
G0: COA Freeze | Any load | ChartFields & Trees define every downstream map
G1: Foundation Config | Master data loads | SetIDs, BUs, Trees, Calendars, FX, Banks exist
G2: Master Data | Open AP/AR, Billing loads | You can’t load open items against missing masters
G3: Books/Profiles in AM | Asset load | FA needs Books & Profiles to value/depreciate
G4: Payment Formats | Payment test | Dispatch requires formats & bank accounts
G5: Statement Loader Config | Bank rec test | Rules depend on statement structure

## DataConv_Objects
Object to load | Prerequisites | Load tool | Exit criteria
ChartField Values | G0–G1 | ExcelToCI: Define Values | 100% rows load; Trees compile; no orphans
Customers (AR) | G1 | ExcelToCI: CUSTOMER | Sample 10 print; dedup pass
Suppliers (AP) | G1 | ExcelToCI: VENDOR | Bank fields masked; sample voucher posts
Banks & Accounts | G1 | Banking setup | Payment preview OK; sample stmt ingests
GL History (2022→cut‑off) | CF values & Trees | JRNL_LOAD | TB variance ≤ 0.5% vs legacy
Open AR | Customers | AR Load (ITEM) | Item count & total match legacy
Open AP | Suppliers; payment formats | Voucher Build | Open balance ties; test payment file
Fixed Assets | G3 | ExcelToCI: AM | NBV variance ≤ 0.5%; depreciation test posts
Invoice CSV cycle test | Customers; VAT skeletons | BI Loader | Load → finalise → PDF → GL post
Bank statements cycle test | G5 | EBS Loader | Auto‑rec ≥ 95% on sample day

## Testing_Plan
Phase | Entry Criteria | Scope | Exit Criteria
Unit | Module config complete | CRUD per module; sample postings | 0 Sev‑1 defects
SIT | Conversion #2 done; interfaces ready | E2E P2P + O2C + bank rec + integrations | ≥ 95% pass; retries controlled
UAT | SIT signed; business data ready | Role‑based scenarios; portal invoices; payment run | Business sign‑off; ≤ 5 Sev‑2 open

## Cutover_Plan
Window | Tasks | Owner
Pre‑cut (T‑7 to T‑2) | Freeze masters; final GL snapshot; re‑extract open AP/AR/FA; archive file hashes; switch Coupa targets for smoke; prep PROD endpoints | PMO / Data / Integrations
Blackout (T‑1 to T) | Load final open items/FA; GL deltas; TB ≤ 0.5%; payment file dry‑run; invoice CSV dry‑run; EBS test import | PMO / Module Leads
Go‑live (T) | Open Period 1; unfreeze interfaces; run first nightly batch; Teams comms | Ops / PMO
T+1 to T+3 | Bank statement import; auto‑rec ≥ 95%; day‑1–3 triage; invoice output checks | Treasury / AR / PMO

## Hypercare
Activity | Details | KPI / Exit
Daily triage | 30‑min Teams call, assign/resolution tracking | Issues burn‑down
KPI monitoring | Close days, auto‑rec %, manual JEs | Two consecutive closes hit targets
SLA adherence | Sev‑1: 1h/4h; Sev‑2: 4h/2d | No missed SLA
Knowledge transfer | Ops run‑books, portal SOPs, evidence archive | Support sign‑off

## Risks
Risk | Impact | Mitigation | Owner
Spreadsheet & portal dependency | Delays/errors at ingest & distribution | Standard templates; naming & hashing; portal run‑books; automate where possible | PMO / Ops
Holiday bandwidth | Build/test slips | AP 0.3 FTE; GL 0.2 FTE; Coupa 0.3 FTE contractors | PMO
LER/EMEA compliance & licensing | Late stop/go | Early approvals; confirm module seats & BU limits pre‑PROD | Chris / Suresh / Procurement
Customer master incomplete | Billing blocked | Starter list now; weekly enrichment cadence | Billing Lead
Bank file/statement quirks | Payment rejects / recon failures | Collect samples early; variant mappers; bank UAT window | Treasury

## Deliverables
Category | Deliverables
Design | Config spec pack; Interface maps; Approval matrices; Trees
Data | CF load files; Customer/Supplier templates; FA workbook; Reconciliation sheets
Build | Jobs for JRNL_LOAD, Voucher Build, BI Loader, EBS; Payment formats
Test | Unit/SIT/UAT scripts; defect log; evidence pack
Cut‑over | Run‑book; file inventory & hashes; go/no‑go checklist
Ops | Teams alerting; archive policy; support rota

## Jira_Backlog
Epic | Story | Description
EPIC‑FOUNDATION | PS‑101 CF load | Load ChartField values via ExcelToCI
EPIC‑FOUNDATION | PS‑102 Trees | Build and compile Trees
EPIC‑FOUNDATION | PS‑103 BUs | Create BUs and SetID control
EPIC‑FOUNDATION | PS‑104 Banks | Create bank shells and map to BUs
EPIC‑GL | GL‑201 Ledger group | Configure ACTUALS (Multi‑Book optional)
EPIC‑GL | GL‑202 AWE | Journal approval thresholds
EPIC‑GL | GL‑203 FX rates | Rate types and tables
EPIC‑AP | AP‑301 Match rules | 2/3‑way rules and tolerances
EPIC‑AP | AP‑302 Pay formats | BACS/SEPA/ACH formats
EPIC‑AP | AP‑303 AWE voucher | Voucher approval path
EPIC‑BI/AR | BI‑401 Loader template | Invoice CSV and BI Loader
EPIC‑BI/AR | BI‑402 PDF/email | BI Publisher invoice output
EPIC‑BI/AR | BI‑403 Portal SOP | Portal upload process & evidence
EPIC‑EBS | CM‑501 Statement mapping | MT940/CAMT/BAI2 variants
EPIC‑EBS | CM‑502 Auto‑rec rules | Reconciliation tolerances
EPIC‑CONV | CV‑601 Masters | Customers/Suppliers/Banks
EPIC‑CONV | CV‑602 History TB | GL 2022→cut‑off
EPIC‑CONV | CV‑603 Open items | Open AP/AR loads
EPIC‑CONV | CV‑604 Fixed Assets | FA master & NBV check
EPIC‑TEST | TS‑701 Unit suite | Module CRUD & smoke
EPIC‑TEST | TS‑702 SIT E2E | Integrations & bank rec
EPIC‑TEST | TS‑703 UAT sign‑off | Business scenarios
EPIC‑CUTOVER | CO‑801 Dry‑run | Final rehearsal
EPIC‑CUTOVER | CO‑802 Go/no‑go | Checklist and approvals
EPIC‑CUTOVER | CO‑803 Day‑1 ops | Monitoring & triage
EPIC‑OPS | OP‑901 Teams alerts | Notifications for loads/failures
EPIC‑OPS | OP‑902 Archive policy | Evidence retention

## Comms_Governance
Item | Details
Teams workspace | Channel “Bonafide – Go Live” with tabs: Index, Risks, Issues, Decisions, Run‑books, Evidence
Steering cadence | Weekly 30 min; stage gates at Foundation, SIT, UAT, Parallel Close
Reporting | Weekly RAG; KPI tiles (close days, auto‑rec %, manual JEs)

## KPIs
KPI | Target | Measurement
Days‑to‑Close | ≤ 5 days | Period close calendar; signed TB
Bank Auto‑rec % | ≥ 95 % | EBS reconciliation summary
Invoice accuracy | ≥ 99 % | BI invoice error rate
Manual journals/month | < 50 | GL JE counts

## Assumptions
Assumption
Coupa remains S2P; NetSuite retired for in‑scope entities post go‑live
No tax engine/treasury hub in Phase‑1; bank portals/file exchange continue
LER/EMEA approvals and licensing confirmed before PROD BU creation

## Next_Steps
Step | Owner | Due
LER/EMEA sign‑off email & file | Chris / Suresh
LOB→LDR dependency one‑pager | Johnny
License snapshot (module seats, BU limits) | Procurement / Larry
Create AT/PT BUs + load CF/Trees (non‑prod) | Sys Admin / GL Lead
Deliver starter customer/vendor lists (AT/PT) | Chris / Suresh